## Activity Tracker (USP)
| Site Launch Activity Tracker |  |  |  | PROGRESS |  | Domain Names |  | 200
| Pre-Launch | 2022-10-19 | 09:00:00.000 |  | 0% | 1 - Pre-Launch | Live Site | <sitename>
| Dry Run | 2022-10-25 | 10:00:00.0000000000015975 |  | 0% | 2 - Dry Run | PROD / Subfolder | prod.arctic.novartis.com/biome | /biome
| Launch | 2022-10-31 | 10:00:00.0000000000015975 |  | 0% | 3 - Launch | Dry-Run Live site | dry-run654.novartis.com
[5 empty] | 0% | 4 - Rollback
[5 empty] | 0% | 5 - Hypercare
[5 empty] | 100% | Dummy
ID | Phase | Predecessor | Start Date | Start Time UTC | Duration | End Date / Time UTC | Task | Site | Owner(s) | Status | Description / Remarks | Improvements
88 | 1 - Pre-Launch |  | 2022-10-19 | 09:00:00.000 | PT0H0M0.001S | 2022-10-19T09:00:00.0010001705959439277525 | Beginning of pre-launch activities | - | All | Pending
83 | 1 - Pre-Launch | 88 | 2022-10-19 | 09:00:00.0010001705959439277525 | PT0H15M0.000S | 2022-10-19T09:15:00.00099996104836575 | Final validation of domain names and DNS settings | - | DevOps | Pending
71 | 1 - Pre-Launch | 88 | 2022-10-19 | 09:00:00.0010001705959439277525 | PT0H15M0.000S | 2022-10-19T09:15:00.00099996104836575 | Module review (Recommendations around modules to be disabled on prod env) | <sitename1-internalurl> | Dev Team | Pending
84 | 1 - Pre-Launch | 83 | 2022-10-19 | 09:15:00.00099996104836575 | PT0H15M0.000S | 2022-10-19T09:30:00.00099975150078300 | Validate CDN configuration | - | DevOps | Pending
72 | 1 - Pre-Launch | 71 | 2022-10-19 | 09:15:00.00099996104836575 | PT0H15M0.000S | 2022-10-19T09:30:00.00099975150078300 | Check the Acquia Search settings are correctly able to connect to solr server. | <sitename1-internalurl> | Dev Team | Pending
68 | 1 - Pre-Launch | 71 | 2022-10-19 | 09:15:00.00099996104836575 | PT0H15M0.000S | 2022-10-19T09:30:00.00099975150078300 | Final review of security updates to core and contrib | <sitename1-internalurl> | Dev Team | Pending
55 | 1 - Pre-Launch | 84 | 2022-10-19 | 09:30:00.00099975150078300 | PT1H0M0.000S | 2022-10-19T10:30:00.0009995419532060622900 | Share the existing CloudFlare rules for <sitename> to the Transition Lead | <sitename1> | DevOps | Pending
66 | 1 - Pre-Launch | 55 | 2022-10-19 | 10:30:00.0009995419532060622900 | PT1H0M0.000S | 2022-10-19T11:30:00.00099933240562425 | Caching configuration validation (JS/CSS aggregation, Memcache, cache bins, cache TTLs, etc.) | <sitename1-internalurl> | Dev Team | Pending
60 | 1 - Pre-Launch | 55 | 2022-10-19 | 10:30:00.0009995419532060622900 | PT2H0M0.000S | 2022-10-19T12:30:00.00099975150078300 | Clean-up of test content | <sitename1-internalurl> | Transition Lead | Pending
80 | 1 - Pre-Launch | 66 | 2022-10-19 | 11:30:00.00099933240562425 | PT0H15M0.000S | 2022-10-19T11:45:00.00099912285804825 | Validate correct SSL configuration in place | <sitename1> | Dev Team | Pending
73 | 1 - Pre-Launch | 80 | 2022-10-19 | 11:45:00.00099912285804825 | PT0H15M0.000S | 2022-10-19T12:00:00.0009989133104681968950 | Review footer menus settings | <sitename1-internalurl> | Dev Team | Pending
62 | 1 - Pre-Launch | 73 | 2022-10-19 | 12:00:00.0009989133104681968950 | PT1H0M0.000S | 2022-10-19T13:00:00.00099870376288950 | Confirm cron enabled and firing successfully | - | Dev Team | Pending
27 | 1 - Pre-Launch | 62 | 2022-10-19 | 13:00:00.00099870376288950 | PT1H0M0.000S | 2022-10-19T14:00:00.00099849421530675 | Identify the CloudFlare rules to disable as part of the launch and share the details to CoE | - | Transition Lead | Pending
74 | 1 - Pre-Launch | 27 | 2022-10-19 | 14:00:00.00099849421530675 | PT0H15M0.000S | 2022-10-19T14:15:00.0009982846677303314325 | Site information Front page URL, E-Mail id and name | <sitename1-internalurl> | Transition Lead | Pending
65 | 1 - Pre-Launch | 27 | 2022-10-19 | 14:00:00.00099849421530675 | PT2H0M0.000S | 2022-10-19T16:00:00.00099870376288950 | Verify platform hardware and software configurations (sizing, APC, Varnish etc) | <sitename1-internalurl> | Acquia (TAM) CoE | Pending
76 | 1 - Pre-Launch | 74 | 2022-10-19 | 14:15:00.0009982846677303314325 | PT0H15M0.000S | 2022-10-19T14:30:00.00099807512014800 | Adjust outgoing notification email address as needed, e.g. <client-donotreply@sitename.com> | <sitename1-internalurl> | Transition Lead Dev Ops | Pending
63 | 1 - Pre-Launch | 76 | 2022-10-19 | 14:30:00.00099807512014800 | PT0H15M0.000S | 2022-10-19T14:45:00.00099786557257200 | Ensure that GTM ID is correctly set and Google Analytics receives the data & Taliem setup is correct and data is collected | <sitename1-internalurl> | Transition Lead | Pending
64 | 1 - Pre-Launch | 63 | 2022-10-19 | 14:45:00.00099786557257200 | PT1H0M0.000S | 2022-10-19T15:45:00.0009976560249924659700 | Confirm that all integration points with 3rd parties are pointing to provider's PROD environment | <sitename1-internalurl> | Transition Lead | Pending
1 | 1 - Pre-Launch | 64 | 2022-10-19 | 15:45:00.0009976560249924659700 | PT1H30M0.000S | 2022-10-19T17:15:00.0009976560249924659700 | Create and share the redirects to CoE | <sitename1> | Transition Lead | Pending
61 | 1 - Pre-Launch | 65 | 2022-10-19 | 16:00:00.00099870376288950 | PT4H0M0.000S | 2022-10-19T20:00:00.00099849421530675 | Confirm Insight Score, review recommendations | - | Dev Team | Pending
75 | 1 - Pre-Launch | 1 | 2022-10-19 | 17:15:00.0009976560249924659700 | PT0H15M0.000S | 2022-10-19T17:15:00.0009976560249924659700 | Configure domain for Recaptcha | <sitename1-internalurl> | Dev Team | Not Applicable
85 | 1 - Pre-Launch | 1 | 2022-10-19 | 17:15:00.0009976560249924659700 | PT0H10M0.000S | 2022-10-19T17:25:00.00099772587418575 | Enable New Relic (confirm data recording) | - | DevOps | Pending
67 | 1 - Pre-Launch | 1 | 2022-10-19 | 17:15:00.0009976560249924659700 | PT0H15M0.000S | 2022-10-19T17:30:00.00099744647741325 | Rename admin user (do not leave as admin) | <sitename1-internalurl> | Dev Team Transition Lead | Pending
2 | 1 - Pre-Launch | 1 | 2022-10-19 | 17:15:00.0009976560249924659700 | PT0H30M0.000S | 2022-10-19T17:45:00.00099786557257200 | Implement the shared redirects in CloudFlare, but leave them as disabled | - | CoE | Pending
4 | 1 - Pre-Launch | 1 | 2022-10-19 | 17:15:00.0009976560249924659700 | PT0H30M0.000S | 2022-10-19T17:45:00.00099786557257200 | Run Link check against PROD environment | <sitename1-internalurl> | Transition Lead | Pending | Ensure that no URLs are hard coded to STG, QA, DEV, or www environments. Validate redirects at Drupal level
56 | 1 - Pre-Launch | 85 | 2022-10-19 | 17:25:00.00099772587418575 | PT8H0M0.000S | 2022-10-20T01:25:00.00099793542176175 | Drupal site performance audit | <sitename1-internalurl> | CoE | Pending
57 | 1 - Pre-Launch | 85 | 2022-10-19 | 17:25:00.00099772587418575 | PT48H0M0.000S | 2022-10-21T17:25:00.00099772587418575 | Load Testing | <sitename1-internalurl> | CoE | Pending
69 | 1 - Pre-Launch | 67 | 2022-10-19 | 17:30:00.00099744647741325 | PT0H15M0.000S | 2022-10-19T17:45:00.00099723692983725 | Disable UID 1 | <sitename1-internalurl> | Dev Team | Pending
70 | 1 - Pre-Launch | 69 | 2022-10-19 | 17:45:00.00099723692983725 | PT0H15M0.000S | 2022-10-19T18:00:00.0009970273822546005075 | Disable test accounts | <sitename1-internalurl> | Transition Lead | Pending
5 | 1 - Pre-Launch | 4 | 2022-10-19 | 17:45:00.00099786557257200 | PT1H0M0.000S | 2022-10-19T18:45:00.0009976560249924659700 | Correct Link check findings | <sitename1-internalurl> | Transition Lead | Pending
59 | 1 - Pre-Launch | 5 | 2022-10-19 | 18:45:00.0009976560249924659700 | PT2H0M0.000S | 2022-10-19T20:45:00.00099786557257200 | Content Review and Sign-off | <sitename1-internalurl> | Transition Lead Site Owner | Pending
81 | 1 - Pre-Launch | 59 | 2022-10-19 | 20:45:00.00099786557257200 | PT4H0M0.000S | 2022-10-20T00:45:00.0009976560249924659700 | Request OneTrust team for initial scan | <sitename1-internalurl> | Transition Lead | Pending
86 | 1 - Pre-Launch | 57 | 2022-10-21 | 17:25:00.00099772587418575 | PT1H0M0.000S | 2022-10-21T18:25:00.00099751632660300 | Final review of logged errors, warnings, and notices | - | DevOps | Pending
58 | 1 - Pre-Launch | 86 | 2022-10-21 | 18:25:00.00099751632660300 | PT48H0M0.000S | 2022-10-23T18:25:00.00099751632660300 | Remediation of Audits and Tests | - |  | Pending
17 | 2 - Dry Run |  | 2022-10-25 | 09:00:00.000 | PT0H30M0.000S | 2022-10-25T09:00:00.000 | Create content DB Backup | <sitename1-internalurl> | CoE | Cancelled
6 | 2 - Dry Run |  | 2022-10-25 | 10:00:00.0000000000015975 | PT0H0M0.001S | 2022-10-25T09:59:59.99999979045242400 | Beginning of Dry Run Meeting | - | Transition Lead | Cancelled | Do we have a list of Dry run activities or is it the dummy url we talked about and purely Content activity ?
3 | 2 - Dry Run | 6 | 2022-10-25 | 09:59:59.99999979045242400 | PT0H5M0.000S | 2022-10-25T09:59:59.99999979045242400 | Review of dry run activities | - | Transition Lead | Cancelled
16 | 2 - Dry Run | 6 | 2022-10-25 | 09:59:59.99999979045242400 | PT0H10M0.000S | 2022-10-25T09:59:59.99999979045242400 | Review of dry-run findings and prioritization of remediation actions | - | Transition Lead | Cancelled
8 | 2 - Dry Run | 16 | 2022-10-25 | 09:59:59.99999979045242400 | PT0H0M0.000S | 2022-10-25T09:59:59.99999979045242400 | End of Dry Run Meeting | - | Transition Lead | Cancelled
18 | 3 - Launch |  | 2022-10-31 | 08:00:00.0000000000031950 | PT0H30M0.000S | 2022-10-31T08:30:00.00000041909515875 | Create content DB Backup for all sites already in PROD | <sitename1-internalurl> | CoE | Pending
87 | 3 - Launch | 18 | 2022-10-31 | 08:30:00.00000041909515875 | PT0H5M0.000S | 2022-10-31T08:30:00.00000041909515875 | Validate SSL configuration | <sitename1> | Dev Team | Not Applicable
77 | 3 - Launch | 18 | 2022-10-31 | 08:30:00.00000041909515875 | PT0H15M0.000S | 2022-10-31T08:45:00.00000020954757600 | Deploy - Switch the code to approved tag | <sitename1-internalurl> | Dev Team | Pending
78 | 3 - Launch | 77 | 2022-10-31 | 08:45:00.00000020954757600 | PT0H15M0.000S | 2022-10-31T09:00:00.000 | Clear Varnish | <sitename1-internalurl> | Dev Ops | Pending
79 | 3 - Launch | 78 | 2022-10-31 | 09:00:00.000 | PT0H15M0.000S | 2022-10-31T09:14:59.99999979045242400 | Validate that user login is working | <sitename1-internalurl> | Transition Lead Site Owner | Pending
7 | 3 - Launch |  | 2022-10-31 | 10:00:00.0000000000015975 | PT0H0M0.001S | 2022-10-31T10:00:00.00099996104836575 | Beginning of Launch Meeting | - | All | Pending
19 | 3 - Launch | 7 | 2022-10-31 | 10:00:00.00099996104836575 | PT0H3M0.000S | 2022-10-31T10:03:00.00099991913884650 | Summarize launch meeting agenda and tasks | - | Transition Lead | Pending
20 | 3 - Launch | 19 | 2022-10-31 | 10:03:00.00099991913884650 | PT0H3M0.000S | 2022-10-31T10:06:00.00099987722933400 | Summarize scope of hypercare | - | Transition Lead | Pending
21 | 3 - Launch | 20 | 2022-10-31 | 10:06:00.00099987722933400 | PT0H1M0.000S | 2022-10-31T10:07:00.00100007280707475 | Get green light from Development - CoE | - | Technical Product Owner | Pending
22 | 3 - Launch | 21 | 2022-10-31 | 10:07:00.00100007280707475 | PT0H1M0.000S | 2022-10-31T10:08:00.001000268384814150 | Get green light from Platform - Acquia | - | Acquia | Pending
23 | 3 - Launch | 22 | 2022-10-31 | 10:08:00.001000268384814150 | PT0H1M0.000S | 2022-10-31T10:09:00.00100046396255625 | Get green light from Governance | - | CoE | Pending | Should this be including Security and perfromance review tasks from "Week of Launch"?
24 | 3 - Launch | 23 | 2022-10-31 | 10:09:00.00100046396255625 | PT0H1M0.000S | 2022-10-31T10:10:00.00100065954029700 | Get green light from Transition Lead | - | Transition Lead | Pending | Should this be validating that all steps have been completed as part of "Week of launch" ? activity like: - Launch Readiness - Configuration review
25 | 3 - Launch | 24 | 2022-10-31 | 10:10:00.00100065954029700 | PT0H1M0.000S | 2022-10-31T10:11:00.00100085511803775 | Get green light from site owner | - | Site Owner | Pending
28 | 3 - Launch | 24 | 2022-10-31 | 10:10:00.00100065954029700 | PT0H1M0.000S | 2022-10-31T10:11:00.00100085511803775 | Give overall green light to start launch process | - | Transition Lead | Pending
26 | 3 - Launch | 28 | 2022-10-31 | 10:11:00.00100085511803775 | PT0H1M0.000S | 2022-10-31T10:12:00.00100105069577850 | Confirm completion of content DB Backup | <sitename1-internalurl> | Transition Lead | Pending
29 | 3 - Launch | 26 | 2022-10-31 | 10:12:00.00100105069577850 | PT0H1M0.000S | 2022-10-31T10:13:00.00100124627351925 | NA | - | CoE | Pending | This Mapping has to be done in Acquia cloud domain level, in Cloudflare existing mapping should work fine
30 | 3 - Launch | 29 | 2022-10-31 | 10:13:00.00100124627351925 | PT0H1M0.000S | 2022-10-31T10:14:00.0010014418512600 | In a new browser window, pre-fill CloudFlare form to create new mapping between '<sitename>' and 'prod.arctic.novartis.com/biome'. | - | CoE | Pending | This Mapping has to be done in Acquia cloud domain level, in Cloudflare existing mapping should work fine
31 | 3 - Launch | 30 | 2022-10-31 | 10:14:00.0010014418512600 | PT0H2M0.000S | 2022-10-31T10:16:00.00100120436400 | In a new browser window, pre-fill CloudFlare form to create rule to redirect traffic from '/biome/xxx' to '/xxx' | - | CoE | Pending
38 | 3 - Launch | 31 | 2022-10-31 | 10:16:00.00100120436400 | PT0H1M0.000S | 2022-10-31T10:17:00.00100139994174075 | Open CloudFlare Window to disable relevant exisiting legacy redirect rules on '<sitename>' (Beluga). | - | CoE | Pending
32 | 3 - Launch | 38 | 2022-10-31 | 10:17:00.00100139994174075 | PT0H2M0.000S | 2022-10-31T10:19:00.001001162454486150 | Disable shield on 'prod.arctic.novartis.com/biome' | <sitename1> | CoE | Pending
33 | 3 - Launch | 32 | 2022-10-31 | 10:19:00.001001162454486150 | PT0H0M5.000S | 2022-10-31T10:19:05.001001073978841300 | NA | - | CoE | Pending
34 | 3 - Launch | 33 | 2022-10-31 | 10:19:05.001001073978841300 | PT0H0M5.000S | 2022-10-31T10:19:10.001000985503196450 | Submit pre-filled CloudFlare form to create new mapping between '<sitename>' and 'prod.arctic.novartis.com/biome'. | - | CoE | Pending
35 | 3 - Launch | 34 | 2022-10-31 | 10:19:10.001000985503196450 | PT0H0M5.000S | 2022-10-31T10:19:15.001000897027552275 | Submit pre-filled CloudFlare form to create rule to redirect traffic from '/biome/xxx' to '/xxx' | - | CoE | Pending
37 | 3 - Launch | 35 | 2022-10-31 | 10:19:15.001000897027552275 | PT0H0M45.000S | 2022-10-31T10:20:00.00100072938948675 | Disable necessary redirect rules from CloudFlare relate to the legacy '<sitename>' site on Beluga | <sitename1> | CoE | Pending
36 | 3 - Launch | 37 | 2022-10-31 | 10:20:00.00100072938948675 | PT0H2M0.000S | 2022-10-31T10:22:00.00100049190223350 | Flash necessary caches (CloudFlare, Drupal, Varnish, ....) | - | CoE | Pending |  | These steps should not be required as part of Go-live
39 | 3 - Launch | 36 | 2022-10-31 | 10:22:00.00100049190223350 | PT0H1M0.000S | 2022-10-31T10:23:00.00100068747997425 | Validate that the new site is live under the url '<sitename>' | <sitename1> | All | Pending
44 | 3 - Launch | 39 | 2022-10-31 | 10:23:00.00100068747997425 | PT0H2M0.000S | 2022-10-31T10:25:00.00100044999271425 | Validate that cookie banner is correctly triggered when accessing the site in anonymous mode | <sitename1> | Transition Lead Business | Pending
47 | 3 - Launch | 39 | 2022-10-31 | 10:23:00.00100068747997425 | PT0H15M0.000S | 2022-10-31T10:38:00.00100047793239150 | Ensure that all redirects are in place and working as expected | <sitename1> | Transition Lead Business | Pending
40 | 3 - Launch | 47 | 2022-10-31 | 10:38:00.00100047793239150 | PT0H10M0.000S | 2022-10-31T10:48:00.00100054778158800 | Perform a visual check, navigating through the pages of '<sitename>' to ensure that everything looks OK | <sitename1> | Transition Lead Site Owner | Pending
41 | 3 - Launch | 40 | 2022-10-31 | 10:48:00.00100054778158800 | PT0H1M0.000S | 2022-10-31T10:49:00.00100074335932875 | Ensure that SSL certificates for '<sitename>' are correct - browser shows a full lock next to the URL field | <sitename1> | Transition Lead Business | Pending
48 | 3 - Launch | 40 | 2022-10-31 | 10:48:00.00100054778158800 | PT0H3M0.000S | 2022-10-31T10:51:00.00100050587206875 | Check that the internal search works as expected | <sitename1> | Transition Lead Business | Pending
45 | 3 - Launch | 40 | 2022-10-31 | 10:48:00.00100054778158800 | PT0H30M0.000S | 2022-10-31T11:18:00.00100075732916400 | Run Link check against live environnment '<sitename>' | <sitename1> | Transition Lead | Pending | Uncover any broken links or links pointing to the back-end (e.g. https://prod.arctic.novartis.com )
42 | 3 - Launch | 41 | 2022-10-31 | 10:49:00.00100074335932875 | PT0H1M0.000S | 2022-10-31T10:50:00.00100093893706950 | Ensure that accessing the live site through http:// redirects visitor to https:// | <sitename1> | Transition Lead Business | Pending
50 | 3 - Launch | 48 | 2022-10-31 | 10:51:00.00100050587206875 | PT0H3M0.000S | 2022-10-31T10:51:00.00100050587206875 | Ensure that the job search works as expected | <sitename1> | Transition Lead Business | Not Applicable
51 | 3 - Launch | 50 | 2022-10-31 | 10:51:00.00100050587206875 | PT0H3M0.000S | 2022-10-31T10:51:00.00100050587206875 | Ensure that the news archive works as expected | <sitename1> | Transition Lead Business | Not Applicable
46 | 3 - Launch | 51 | 2022-10-31 | 10:51:00.00100050587206875 | PT0H5M0.000S | 2022-10-31T10:56:00.00100022647529625 | Ensure that Google Analytics receives the click data from the live site. | <sitename1> | Transition Lead Business | Pending
15 | 3 - Launch | 46 | 2022-10-31 | 10:56:00.00100022647529625 | PT0H15M0.000S | 2022-10-31T11:11:00.00100001692772025 | Review of the launch validation findings and prioritization | - | Transition Lead Site Owner | Pending
14 | 3 - Launch | 15 | 2022-10-31 | 11:11:00.00100001692772025 | PT0H3M0.000S | 2022-10-31T11:14:00.00099997501820100 | Acceptance of the site by the site owner | <sitename1> | Site Owner | Pending
52 | 3 - Launch | 14 | 2022-10-31 | 11:14:00.00099997501820100 | PT0H5M0.000S | 2022-10-31T11:14:00.00099997501820100 | Enable shield on legacy site | <sitename1> | Transition Lead Business | Not Applicable
9 | 3 - Launch | 52 | 2022-10-31 | 11:14:00.00099997501820100 | PT0H0M0.001S | 2022-10-31T11:14:00.00200014561414950 | End of Launch Meeting | - | Transition Lead | Pending
43 | 3 - Launch | 9 | 2022-10-31 | 11:14:00.00200014561414950 | PT0H3M0.000S | 2022-10-31T11:17:00.00200010370463025 | Request OneTrust team to re-scan '<sitename>' for new cookie categorization by sending email to operations.onetrust@novartis.com | <sitename1> | Transition Lead | Pending
82 | 3 - Launch | 9 | 2022-10-31 | 11:14:00.00200014561414950 | PT0H15M0.000S | 2022-10-31T11:29:00.00199993606656675 | Add that www and naked domain names are in the Novartis Arctic EMEA docroot from Acquia cloud | <sitename1> | DevOps DevTeam | Pending
54 | 4 - Rollback | 53 | 2022-10-31 | 09:59:59.99999979045242400 | PT0H10M0.000S | 2022-10-31T10:09:59.99999986030161375 | End of Rollback process |  | Transition Lead | Pending
53 | 4 - Rollback |  | 2022-10-31 | 10:00:00.0000000000015975 | PT0H0M0.000S | 2022-10-31T09:59:59.99999979045242400 | Initiate Rollback |  | Transition Lead Site Owner | Pending
10 | 5 - Hypercare | 9 | 2022-10-31 | 11:13:59.00200014561239550 | PT168H0M1.000S | 2022-11-07T11:14:00.00200014561414950 | Beginning of Hypercare | - | Site Owner | Pending
12 | 5 - Hypercare | 9 | 2022-10-31 | 11:14:00.00200014561414950 | PT0H10M0.000S | 2022-10-31T11:24:00.00200021546333925 | Share the "Your Site is Live, Now What" document | - | Transition Lead | Pending
49 | 5 - Hypercare | 10 | 2022-11-02 | 12:00:00.000 | PT0H10M0.000S | 2022-11-02T12:10:00.00000006984918975 | Revalidate cookie banner after completion of the OneTrust rescan | <sitename1> | Transition Lead | Pending
13 | 5 - Hypercare | 10 | 2022-11-07 | 11:14:00.00200014561414950 | PT0H10M0.000S | 2022-11-07T11:24:00.00200021546333925 | Inform the site owner about the end of hypercare | - | Transition Lead | Pending
11 | 5 - Hypercare | 13 | 2022-11-07 | 11:24:00.00200021546333925 | PT0H10M0.000S | 2022-11-07T11:34:00.00200028531253575 | End of Hypercare | - | Site Owner | Pending
89 |  |  | - | - |  | -
90 |  |  | - | - |  | -
91 |  |  | - | - |  | -
92 |  |  | - | - |  | -
93 |  |  | - | - |  | -
94 |  |  | - | - |  | -
95 |  |  | - | - |  | -
96 |  |  | - | - |  | -
97 |  |  | - | - |  | -
98 |  |  | - | - |  | -
99 |  |  | - | - |  | -
100 |  |  | - | - |  | -
101 |  |  | - | - |  | -
102 |  |  | - | - |  | -
103 |  |  | - | - |  | -
104 |  |  | - | - |  | -
105 |  |  | - | - |  | -
106 |  |  | - | - |  | -
107 |  |  | - | - |  | -
108 |  |  | - | - |  | -
109 |  |  | - | - |  | -
110 |  |  | - | - |  | -
111 |  |  | - | - |  | -
112 |  |  | - | - |  | -
113 |  |  | - | - |  | -
114 |  |  | - | - |  | -
115 |  |  | - | - |  | -
116 |  |  | - | - |  | -
117 |  |  | - | - |  | -
118 |  |  | - | - |  | -
119 |  |  | - | - |  | -
120 |  |  | - | - |  | -
121 |  |  | - | - |  | -
122 |  |  | - | - |  | -
123 |  |  | - | - |  | -
124 |  |  | - | - |  | -
125 |  |  | - | - |  | -
126 |  |  | - | - |  | -
127 |  |  | - | - |  | -
128 |  |  | - | - |  | -
129 |  |  | - | - |  | -
130 |  |  | - | - |  | -
131 |  |  | - | - |  | -
132 |  |  | - | - |  | -
133 |  |  | - | - |  | -
134 |  |  | - | - |  | -
135 |  |  | - | - |  | -
136 |  |  | - | - |  | -
137 |  |  | - | - |  | -
138 |  |  | - | - |  | -
139 |  |  | - | - |  | -
140 |  |  | - | - |  | -
141 |  |  | - | - |  | -
142 |  |  | - | - |  | -
143 |  |  | - | - |  | -
144 |  |  | - | - |  | -
145 |  |  | - | - |  | -
146 |  |  | - | - |  | -
147 |  |  | - | - |  | -
148 |  |  | - | - |  | -
149 |  |  | - | - |  | -
150 |  |  | - | - |  | -
151 |  |  | - | - |  | -
152 |  |  | - | - |  | -
153 |  |  | - | - |  | -
154 |  |  | - | - |  | -
155 |  |  | - | - |  | -
156 |  |  | - | - |  | -
157 |  |  | - | - |  | -
158 |  |  | - | - |  | -
159 |  |  | - | - |  | -
160 |  |  | - | - |  | -
161 |  |  | - | - |  | -
162 |  |  | - | - |  | -
163 |  |  | - | - |  | -
164 |  |  | - | - |  | -
165 |  |  | - | - |  | -
166 |  |  | - | - |  | -
167 |  |  | - | - |  | -
168 |  |  | - | - |  | -
169 |  |  | - | - |  | -
170 |  |  | - | - |  | -
171 |  |  | - | - |  | -
172 |  |  | - | - |  | -
173 |  |  | - | - |  | -
174 |  |  | - | - |  | -
175 |  |  | - | - |  | -
176 |  |  | - | - |  | -
177 |  |  | - | - |  | -
178 |  |  | - | - |  | -
179 |  |  | - | - |  | -
180 |  |  | - | - |  | -
181 |  |  | - | - |  | -
182 |  |  | - | - |  | -
183 |  |  | - | - |  | -
184 |  |  | - | - |  | -
185 |  |  | - | - |  | -
186 |  |  | - | - |  | -
187 |  |  | - | - |  | -
188 |  |  | - | - |  | -
189 |  |  | - | - |  | -
190 |  |  | - | - |  | -
191 |  |  | - | - |  | -
192 |  |  | - | - |  | -
193 |  |  | - | - |  | -
194 |  |  | - | - |  | -
195 |  |  | - | - |  | -
196 |  |  | - | - |  | -
197 |  |  | - | - |  | -
198 |  |  | - | - |  | -
199 |  |  | - | - |  | -
200 |  |  | - | - |  | -
Gowni, Karunakar (Ext):
@bikram please confirm if MVP has search feature?
Gowni, Karunakar (Ext):
Since these are new sites, no existing cloudflare rules exists. @bikram to confirm.
Gowni, Karunakar (Ext):
Since these are new sites, no existing cloudflare rules exists. @bikram to confirm.
Gowni, Karunakar (Ext):
Assuming there will be no redirects required as it will be new site and not migration.
Gowni, Karunakar (Ext):
Assuming there will be no redirects required as it will be new site and not migration.
Gowni, Karunakar (Ext):
Is this part of MVP? If not then we can ignore this row for now.
Gowni, Karunakar (Ext):
Ignore this - Specific to Arctic
Gowni, Karunakar (Ext):
Ignore this - Specific to Arctic
Gowni, Karunakar (Ext):
Ignore this - Specific to Arctic
Gowni, Karunakar (Ext):
WE need information on cloudflare rules for each site if any to be setup.
Gowni, Karunakar (Ext):
Arctic Specific
Gowni, Karunakar (Ext):
Only in case of migration. Can ignore if not migration
Gowni, Karunakar (Ext):
Validate if applicable
Note on H14: Gowni, Karunakar (Ext): @bikram please confirm if MVP has search feature?
Note on H16: Gowni, Karunakar (Ext): Since these are new sites, no existing cloudflare rules exists. @bikram to confirm.
Note on H22: Gowni, Karunakar (Ext): Since these are new sites, no existing cloudflare rules exists. @bikram to confirm.
Note on H28: Gowni, Karunakar (Ext): Assuming there will be no redirects required as it will be new site and not migration.
Note on H33: Gowni, Karunakar (Ext): Assuming there will be no redirects required as it will be new site and not migration.
Note on H41: Gowni, Karunakar (Ext): Is this part of MVP? If not then we can ignore this row for now.
Note on H65: Gowni, Karunakar (Ext): Ignore this - Specific to Arctic
Note on H66: Gowni, Karunakar (Ext): Ignore this - Specific to Arctic
Note on H67: Gowni, Karunakar (Ext): Ignore this - Specific to Arctic
Note on H70: Gowni, Karunakar (Ext): WE need information on cloudflare rules for each site if any to be setup.
Note on H71: Gowni, Karunakar (Ext): Arctic Specific
Note on H72: Gowni, Karunakar (Ext): Only in case of migration. Can ignore if not migration
Note on H75: Gowni, Karunakar (Ext): Validate if applicable

## Activity Tracker
| Site Launch Activity Tracker |  |  |  | PROGRESS |  | Domain Names |  | 200
| Pre-Launch | 2021-02-14 | 09:00:00.000 |  | 0% | 1 - Pre-Launch | Live Site | <sitename>
| Dry Run | 2021-02-16 | 10:00:00.0000000000015975 |  | 0% | 2 - Dry Run | PROD / Subfolder | prod.arctic.novartis.com/biome | /biome
| Launch | 2021-02-18 | 10:00:00.0000000000015975 |  | 0% | 3 - Launch | Dry-Run Live site | dry-run654.novartis.com
[5 empty] | 0% | 4 - Rollback
[5 empty] | 0% | 5 - Hypercare
[5 empty] | 100% | Dummy
ID | Phase | Predecessor | Start Date | Start Time UTC | Duration | End Date / Time UTC | Task | Site | Owner(s) | Status | Description / Remarks | Improvements
88 | 1 - Pre-Launch |  | 2021-02-14 | 09:00:00.000 | PT0H0M0.001S | 2021-02-14T09:00:00.0010001705959439277525 | Beginning of pre-launch activities | - | All | Pending
83 | 1 - Pre-Launch | 88 | 2021-02-14 | 09:00:00.0010001705959439277525 | PT0H15M0.000S | 2021-02-14T09:15:00.00099996104836575 | Final validation of domain names and DNS settings | - | DevOps | Pending
71 | 1 - Pre-Launch | 88 | 2021-02-14 | 09:00:00.0010001705959439277525 | PT0H15M0.000S | 2021-02-14T09:15:00.00099996104836575 | Module review (Recommendations around modules to be disabled on prod env) | <sitename1-internalurl> | Dev Team | Pending
84 | 1 - Pre-Launch | 83 | 2021-02-14 | 09:15:00.00099996104836575 | PT0H15M0.000S | 2021-02-14T09:30:00.00099975150078300 | Validate CDN configuration | - | DevOps | Pending
72 | 1 - Pre-Launch | 71 | 2021-02-14 | 09:15:00.00099996104836575 | PT0H15M0.000S | 2021-02-14T09:30:00.00099975150078300 | Check the Acquia Search settings are correctly able to connect to solr server. | <sitename1-internalurl> | Dev Team | Pending
68 | 1 - Pre-Launch | 71 | 2021-02-14 | 09:15:00.00099996104836575 | PT0H15M0.000S | 2021-02-14T09:30:00.00099975150078300 | Final review of security updates to core and contrib | <sitename1-internalurl> | Dev Team | Pending
55 | 1 - Pre-Launch | 84 | 2021-02-14 | 09:30:00.00099975150078300 | PT1H0M0.000S | 2021-02-14T10:30:00.0009995419532060622900 | Share the existing CloudFlare rules for <sitename> to the Transition Lead | <sitename1> | DevOps | Pending
66 | 1 - Pre-Launch | 55 | 2021-02-14 | 10:30:00.0009995419532060622900 | PT1H0M0.000S | 2021-02-14T11:30:00.00099933240562425 | Caching configuration validation (JS/CSS aggregation, Memcache, cache bins, cache TTLs, etc.) | <sitename1-internalurl> | Dev Team | Pending
60 | 1 - Pre-Launch | 55 | 2021-02-14 | 10:30:00.0009995419532060622900 | PT2H0M0.000S | 2021-02-14T12:30:00.00099975150078300 | Clean-up of test content | <sitename1-internalurl> | Transition Lead | Pending
80 | 1 - Pre-Launch | 66 | 2021-02-14 | 11:30:00.00099933240562425 | PT0H15M0.000S | 2021-02-14T11:45:00.00099912285804825 | Validate correct SSL configuration in place | <sitename1> | Dev Team | Pending
73 | 1 - Pre-Launch | 80 | 2021-02-14 | 11:45:00.00099912285804825 | PT0H15M0.000S | 2021-02-14T12:00:00.0009989133104681968950 | Review footer menus settings | <sitename1-internalurl> | Dev Team | Pending
62 | 1 - Pre-Launch | 73 | 2021-02-14 | 12:00:00.0009989133104681968950 | PT1H0M0.000S | 2021-02-14T13:00:00.00099870376288950 | Confirm cron enabled and firing successfully | - | Dev Team | Pending
27 | 1 - Pre-Launch | 62 | 2021-02-14 | 13:00:00.00099870376288950 | PT1H0M0.000S | 2021-02-14T14:00:00.00099849421530675 | Identify the CloudFlare rules to disable as part of the launch and share the details to CoE | - | Transition Lead | Pending
74 | 1 - Pre-Launch | 27 | 2021-02-14 | 14:00:00.00099849421530675 | PT0H15M0.000S | 2021-02-14T14:15:00.0009982846677303314325 | Site information Front page URL, E-Mail id and name | <sitename1-internalurl> | Transition Lead | Pending
65 | 1 - Pre-Launch | 27 | 2021-02-14 | 14:00:00.00099849421530675 | PT2H0M0.000S | 2021-02-14T16:00:00.00099870376288950 | Verify platform hardware and software configurations (sizing, APC, Varnish etc) | <sitename1-internalurl> | Acquia (TAM) CoE | Pending
76 | 1 - Pre-Launch | 74 | 2021-02-14 | 14:15:00.0009982846677303314325 | PT0H15M0.000S | 2021-02-14T14:30:00.00099807512014800 | Adjust outgoing notification email address as needed, e.g. <client-donotreply@sitename.com> | <sitename1-internalurl> | Transition Lead Dev Ops | Pending
63 | 1 - Pre-Launch | 76 | 2021-02-14 | 14:30:00.00099807512014800 | PT0H15M0.000S | 2021-02-14T14:45:00.00099786557257200 | Ensure that GTM ID is correctly set and Google Analytics receives the data & Taliem setup is correct and data is collected | <sitename1-internalurl> | Transition Lead | Pending
64 | 1 - Pre-Launch | 63 | 2021-02-14 | 14:45:00.00099786557257200 | PT1H0M0.000S | 2021-02-14T15:45:00.0009976560249924659700 | Confirm that all integration points with 3rd parties are pointing to provider's PROD environment | <sitename1-internalurl> | Transition Lead | Pending
1 | 1 - Pre-Launch | 64 | 2021-02-14 | 15:45:00.0009976560249924659700 | PT1H30M0.000S | 2021-02-14T17:15:00.0009976560249924659700 | Create and share the redirects to CoE | <sitename1> | Transition Lead | Pending
61 | 1 - Pre-Launch | 65 | 2021-02-14 | 16:00:00.00099870376288950 | PT4H0M0.000S | 2021-02-14T20:00:00.00099849421530675 | Confirm Insight Score, review recommendations | - | Dev Team | Pending
75 | 1 - Pre-Launch | 1 | 2021-02-14 | 17:15:00.0009976560249924659700 | PT0H15M0.000S | 2021-02-14T17:15:00.0009976560249924659700 | Configure domain for Recaptcha | <sitename1-internalurl> | Dev Team | Not Applicable
85 | 1 - Pre-Launch | 1 | 2021-02-14 | 17:15:00.0009976560249924659700 | PT0H10M0.000S | 2021-02-14T17:25:00.00099772587418575 | Enable New Relic (confirm data recording) | - | DevOps | Pending
67 | 1 - Pre-Launch | 1 | 2021-02-14 | 17:15:00.0009976560249924659700 | PT0H15M0.000S | 2021-02-14T17:30:00.00099744647741325 | Rename admin user (do not leave as admin) | <sitename1-internalurl> | Dev Team Transition Lead | Pending
2 | 1 - Pre-Launch | 1 | 2021-02-14 | 17:15:00.0009976560249924659700 | PT0H30M0.000S | 2021-02-14T17:45:00.00099786557257200 | Implement the shared redirects in CloudFlare, but leave them as disabled | - | CoE | Pending
4 | 1 - Pre-Launch | 1 | 2021-02-14 | 17:15:00.0009976560249924659700 | PT0H30M0.000S | 2021-02-14T17:45:00.00099786557257200 | Run Link check against PROD environment | <sitename1-internalurl> | Transition Lead | Pending | Ensure that no URLs are hard coded to STG, QA, DEV, or www environments. Validate redirects at Drupal level
56 | 1 - Pre-Launch | 85 | 2021-02-14 | 17:25:00.00099772587418575 | PT8H0M0.000S | 2021-02-15T01:25:00.00099793542176175 | Drupal site performance audit | <sitename1-internalurl> | CoE | Pending
57 | 1 - Pre-Launch | 85 | 2021-02-14 | 17:25:00.00099772587418575 | PT48H0M0.000S | 2021-02-16T17:25:00.00099772587418575 | Load Testing | <sitename1-internalurl> | CoE | Pending
69 | 1 - Pre-Launch | 67 | 2021-02-14 | 17:30:00.00099744647741325 | PT0H15M0.000S | 2021-02-14T17:45:00.00099723692983725 | Disable UID 1 | <sitename1-internalurl> | Dev Team | Pending
70 | 1 - Pre-Launch | 69 | 2021-02-14 | 17:45:00.00099723692983725 | PT0H15M0.000S | 2021-02-14T18:00:00.0009970273822546005075 | Disable test accounts | <sitename1-internalurl> | Transition Lead | Pending
5 | 1 - Pre-Launch | 4 | 2021-02-14 | 17:45:00.00099786557257200 | PT1H0M0.000S | 2021-02-14T18:45:00.0009976560249924659700 | Correct Link check findings | <sitename1-internalurl> | Transition Lead | Pending
59 | 1 - Pre-Launch | 5 | 2021-02-14 | 18:45:00.0009976560249924659700 | PT2H0M0.000S | 2021-02-14T20:45:00.00099786557257200 | Content Review and Sign-off | <sitename1-internalurl> | Transition Lead Site Owner | Pending
81 | 1 - Pre-Launch | 59 | 2021-02-14 | 20:45:00.00099786557257200 | PT4H0M0.000S | 2021-02-15T00:45:00.0009976560249924659700 | Request OneTrust team for initial scan | <sitename1-internalurl> | Transition Lead | Pending
86 | 1 - Pre-Launch | 57 | 2021-02-16 | 17:25:00.00099772587418575 | PT1H0M0.000S | 2021-02-16T18:25:00.00099751632660300 | Final review of logged errors, warnings, and notices | - | DevOps | Pending
58 | 1 - Pre-Launch | 86 | 2021-02-16 | 18:25:00.00099751632660300 | PT48H0M0.000S | 2021-02-18T18:25:00.00099751632660300 | Remediation of Audits and Tests | - |  | Pending
17 | 2 - Dry Run |  | 2021-02-16 | 09:00:00.000 | PT0H30M0.000S | 2021-02-16T09:00:00.000 | Create content DB Backup | <sitename1-internalurl> | CoE | Cancelled
6 | 2 - Dry Run |  | 2021-02-16 | 10:00:00.0000000000015975 | PT0H0M0.001S | 2021-02-16T09:59:59.99999979045242400 | Beginning of Dry Run Meeting | - | Transition Lead | Cancelled | Do we have a list of Dry run activities or is it the dummy url we talked about and purely Content activity ?
3 | 2 - Dry Run | 6 | 2021-02-16 | 09:59:59.99999979045242400 | PT0H5M0.000S | 2021-02-16T09:59:59.99999979045242400 | Review of dry run activities | - | Transition Lead | Cancelled
16 | 2 - Dry Run | 6 | 2021-02-16 | 09:59:59.99999979045242400 | PT0H10M0.000S | 2021-02-16T09:59:59.99999979045242400 | Review of dry-run findings and prioritization of remediation actions | - | Transition Lead | Cancelled
8 | 2 - Dry Run | 16 | 2021-02-16 | 09:59:59.99999979045242400 | PT0H0M0.000S | 2021-02-16T09:59:59.99999979045242400 | End of Dry Run Meeting | - | Transition Lead | Cancelled
18 | 3 - Launch |  | 2021-02-18 | 08:00:00.0000000000031950 | PT0H30M0.000S | 2021-02-18T08:30:00.00000041909515875 | Create content DB Backup for all sites already in PROD | <sitename1-internalurl> | CoE | Pending
87 | 3 - Launch | 18 | 2021-02-18 | 08:30:00.00000041909515875 | PT0H5M0.000S | 2021-02-18T08:30:00.00000041909515875 | Validate SSL configuration | <sitename1> | Dev Team | Not Applicable
77 | 3 - Launch | 18 | 2021-02-18 | 08:30:00.00000041909515875 | PT0H15M0.000S | 2021-02-18T08:45:00.00000020954757600 | Deploy - Switch the code to approved tag | <sitename1-internalurl> | Dev Team | Pending
78 | 3 - Launch | 77 | 2021-02-18 | 08:45:00.00000020954757600 | PT0H15M0.000S | 2021-02-18T09:00:00.000 | Clear Varnish | <sitename1-internalurl> | Dev Ops | Pending
79 | 3 - Launch | 78 | 2021-02-18 | 09:00:00.000 | PT0H15M0.000S | 2021-02-18T09:14:59.99999979045242400 | Validate that user login is working | <sitename1-internalurl> | Transition Lead Site Owner | Pending
7 | 3 - Launch |  | 2021-02-18 | 10:00:00.0000000000015975 | PT0H0M0.001S | 2021-02-18T10:00:00.00099996104836575 | Beginning of Launch Meeting | - | All | Pending
19 | 3 - Launch | 7 | 2021-02-18 | 10:00:00.00099996104836575 | PT0H3M0.000S | 2021-02-18T10:03:00.00099991913884650 | Summarize launch meeting agenda and tasks | - | Transition Lead | Pending
20 | 3 - Launch | 19 | 2021-02-18 | 10:03:00.00099991913884650 | PT0H3M0.000S | 2021-02-18T10:06:00.00099987722933400 | Summarize scope of hypercare | - | Transition Lead | Pending
21 | 3 - Launch | 20 | 2021-02-18 | 10:06:00.00099987722933400 | PT0H1M0.000S | 2021-02-18T10:07:00.00100007280707475 | Get green light from Development - CoE | - | Technical Product Owner | Pending
22 | 3 - Launch | 21 | 2021-02-18 | 10:07:00.00100007280707475 | PT0H1M0.000S | 2021-02-18T10:08:00.001000268384814150 | Get green light from Platform - Acquia | - | Acquia | Pending
23 | 3 - Launch | 22 | 2021-02-18 | 10:08:00.001000268384814150 | PT0H1M0.000S | 2021-02-18T10:09:00.00100046396255625 | Get green light from Governance | - | CoE | Pending | Should this be including Security and perfromance review tasks from "Week of Launch"?
24 | 3 - Launch | 23 | 2021-02-18 | 10:09:00.00100046396255625 | PT0H1M0.000S | 2021-02-18T10:10:00.00100065954029700 | Get green light from Transition Lead | - | Transition Lead | Pending | Should this be validating that all steps have been completed as part of "Week of launch" ? activity like: - Launch Readiness - Configuration review
25 | 3 - Launch | 24 | 2021-02-18 | 10:10:00.00100065954029700 | PT0H1M0.000S | 2021-02-18T10:11:00.00100085511803775 | Get green light from site owner | - | Site Owner | Pending
28 | 3 - Launch | 24 | 2021-02-18 | 10:10:00.00100065954029700 | PT0H1M0.000S | 2021-02-18T10:11:00.00100085511803775 | Give overall green light to start launch process | - | Transition Lead | Pending
26 | 3 - Launch | 28 | 2021-02-18 | 10:11:00.00100085511803775 | PT0H1M0.000S | 2021-02-18T10:12:00.00100105069577850 | Confirm completion of content DB Backup | <sitename1-internalurl> | Transition Lead | Pending
29 | 3 - Launch | 26 | 2021-02-18 | 10:12:00.00100105069577850 | PT0H1M0.000S | 2021-02-18T10:13:00.00100124627351925 | NA | - | CoE | Pending | This Mapping has to be done in Acquia cloud domain level, in Cloudflare existing mapping should work fine
30 | 3 - Launch | 29 | 2021-02-18 | 10:13:00.00100124627351925 | PT0H1M0.000S | 2021-02-18T10:14:00.0010014418512600 | In a new browser window, pre-fill CloudFlare form to create new mapping between '<sitename>' and 'prod.arctic.novartis.com/biome'. | - | CoE | Pending | This Mapping has to be done in Acquia cloud domain level, in Cloudflare existing mapping should work fine
31 | 3 - Launch | 30 | 2021-02-18 | 10:14:00.0010014418512600 | PT0H2M0.000S | 2021-02-18T10:16:00.00100120436400 | In a new browser window, pre-fill CloudFlare form to create rule to redirect traffic from '/biome/xxx' to '/xxx' | - | CoE | Pending
38 | 3 - Launch | 31 | 2021-02-18 | 10:16:00.00100120436400 | PT0H1M0.000S | 2021-02-18T10:17:00.00100139994174075 | Open CloudFlare Window to disable relevant exisiting legacy redirect rules on '<sitename>' (Beluga). | - | CoE | Pending
32 | 3 - Launch | 38 | 2021-02-18 | 10:17:00.00100139994174075 | PT0H2M0.000S | 2021-02-18T10:19:00.001001162454486150 | Disable shield on 'prod.arctic.novartis.com/biome' | <sitename1> | CoE | Pending
33 | 3 - Launch | 32 | 2021-02-18 | 10:19:00.001001162454486150 | PT0H0M5.000S | 2021-02-18T10:19:05.001001073978841300 | NA | - | CoE | Pending
34 | 3 - Launch | 33 | 2021-02-18 | 10:19:05.001001073978841300 | PT0H0M5.000S | 2021-02-18T10:19:10.001000985503196450 | Submit pre-filled CloudFlare form to create new mapping between '<sitename>' and 'prod.arctic.novartis.com/biome'. | - | CoE | Pending
35 | 3 - Launch | 34 | 2021-02-18 | 10:19:10.001000985503196450 | PT0H0M5.000S | 2021-02-18T10:19:15.001000897027552275 | Submit pre-filled CloudFlare form to create rule to redirect traffic from '/biome/xxx' to '/xxx' | - | CoE | Pending
37 | 3 - Launch | 35 | 2021-02-18 | 10:19:15.001000897027552275 | PT0H0M45.000S | 2021-02-18T10:20:00.00100072938948675 | Disable necessary redirect rules from CloudFlare relate to the legacy '<sitename>' site on Beluga | <sitename1> | CoE | Pending
36 | 3 - Launch | 37 | 2021-02-18 | 10:20:00.00100072938948675 | PT0H2M0.000S | 2021-02-18T10:22:00.00100049190223350 | Flash necessary caches (CloudFlare, Drupal, Varnish, ....) | - | CoE | Pending |  | These steps should not be required as part of Go-live
39 | 3 - Launch | 36 | 2021-02-18 | 10:22:00.00100049190223350 | PT0H1M0.000S | 2021-02-18T10:23:00.00100068747997425 | Validate that the new site is live under the url '<sitename>' | <sitename1> | All | Pending
44 | 3 - Launch | 39 | 2021-02-18 | 10:23:00.00100068747997425 | PT0H2M0.000S | 2021-02-18T10:25:00.00100044999271425 | Validate that cookie banner is correctly triggered when accessing the site in anonymous mode | <sitename1> | Transition Lead Business | Pending
47 | 3 - Launch | 39 | 2021-02-18 | 10:23:00.00100068747997425 | PT0H15M0.000S | 2021-02-18T10:38:00.00100047793239150 | Ensure that all redirects are in place and working as expected | <sitename1> | Transition Lead Business | Pending
40 | 3 - Launch | 47 | 2021-02-18 | 10:38:00.00100047793239150 | PT0H10M0.000S | 2021-02-18T10:48:00.00100054778158800 | Perform a visual check, navigating through the pages of '<sitename>' to ensure that everything looks OK | <sitename1> | Transition Lead Site Owner | Pending
41 | 3 - Launch | 40 | 2021-02-18 | 10:48:00.00100054778158800 | PT0H1M0.000S | 2021-02-18T10:49:00.00100074335932875 | Ensure that SSL certificates for '<sitename>' are correct - browser shows a full lock next to the URL field | <sitename1> | Transition Lead Business | Pending
48 | 3 - Launch | 40 | 2021-02-18 | 10:48:00.00100054778158800 | PT0H3M0.000S | 2021-02-18T10:51:00.00100050587206875 | Check that the internal search works as expected | <sitename1> | Transition Lead Business | Pending
45 | 3 - Launch | 40 | 2021-02-18 | 10:48:00.00100054778158800 | PT0H30M0.000S | 2021-02-18T11:18:00.00100075732916400 | Run Link check against live environnment '<sitename>' | <sitename1> | Transition Lead | Pending | Uncover any broken links or links pointing to the back-end (e.g. https://prod.arctic.novartis.com )
42 | 3 - Launch | 41 | 2021-02-18 | 10:49:00.00100074335932875 | PT0H1M0.000S | 2021-02-18T10:50:00.00100093893706950 | Ensure that accessing the live site through http:// redirects visitor to https:// | <sitename1> | Transition Lead Business | Pending
50 | 3 - Launch | 48 | 2021-02-18 | 10:51:00.00100050587206875 | PT0H3M0.000S | 2021-02-18T10:51:00.00100050587206875 | Ensure that the job search works as expected | <sitename1> | Transition Lead Business | Not Applicable
51 | 3 - Launch | 50 | 2021-02-18 | 10:51:00.00100050587206875 | PT0H3M0.000S | 2021-02-18T10:51:00.00100050587206875 | Ensure that the news archive works as expected | <sitename1> | Transition Lead Business | Not Applicable
46 | 3 - Launch | 51 | 2021-02-18 | 10:51:00.00100050587206875 | PT0H5M0.000S | 2021-02-18T10:56:00.00100022647529625 | Ensure that Google Analytics receives the click data from the live site. | <sitename1> | Transition Lead Business | Pending
15 | 3 - Launch | 46 | 2021-02-18 | 10:56:00.00100022647529625 | PT0H15M0.000S | 2021-02-18T11:11:00.00100001692772025 | Review of the launch validation findings and prioritization | - | Transition Lead Site Owner | Pending
14 | 3 - Launch | 15 | 2021-02-18 | 11:11:00.00100001692772025 | PT0H3M0.000S | 2021-02-18T11:14:00.00099997501820100 | Acceptance of the site by the site owner | <sitename1> | Site Owner | Pending
52 | 3 - Launch | 14 | 2021-02-18 | 11:14:00.00099997501820100 | PT0H5M0.000S | 2021-02-18T11:14:00.00099997501820100 | Enable shield on legacy site | <sitename1> | Transition Lead Business | Not Applicable
9 | 3 - Launch | 52 | 2021-02-18 | 11:14:00.00099997501820100 | PT0H0M0.001S | 2021-02-18T11:14:00.00200014561414950 | End of Launch Meeting | - | Transition Lead | Pending
43 | 3 - Launch | 9 | 2021-02-18 | 11:14:00.00200014561414950 | PT0H3M0.000S | 2021-02-18T11:17:00.00200010370463025 | Request OneTrust team to re-scan '<sitename>' for new cookie categorization by sending email to operations.onetrust@novartis.com | <sitename1> | Transition Lead | Pending
82 | 3 - Launch | 9 | 2021-02-18 | 11:14:00.00200014561414950 | PT0H15M0.000S | 2021-02-18T11:29:00.00199993606656675 | Add that www and naked domain names are in the Novartis Arctic EMEA docroot from Acquia cloud | <sitename1> | DevOps DevTeam | Pending
54 | 4 - Rollback | 53 | 2021-02-18 | 09:59:59.99999979045242400 | PT0H10M0.000S | 2021-02-18T10:09:59.99999986030161375 | End of Rollback process |  | Transition Lead | Pending
53 | 4 - Rollback |  | 2021-02-18 | 10:00:00.0000000000015975 | PT0H0M0.000S | 2021-02-18T09:59:59.99999979045242400 | Initiate Rollback |  | Transition Lead Site Owner | Pending
10 | 5 - Hypercare | 9 | 2021-02-18 | 11:13:59.00200014561239550 | PT168H0M1.000S | 2021-02-25T11:14:00.00200014561414950 | Beginning of Hypercare | - | Site Owner | Pending
12 | 5 - Hypercare | 9 | 2021-02-18 | 11:14:00.00200014561414950 | PT0H10M0.000S | 2021-02-18T11:24:00.00200021546333925 | Share the "Your Site is Live, Now What" document | - | Transition Lead | Pending
49 | 5 - Hypercare | 10 | 2021-02-20 | 12:00:00.000 | PT0H10M0.000S | 2021-02-20T12:10:00.00000006984918975 | Revalidate cookie banner after completion of the OneTrust rescan | <sitename1> | Transition Lead | Pending
13 | 5 - Hypercare | 10 | 2021-02-25 | 11:14:00.00200014561414950 | PT0H10M0.000S | 2021-02-25T11:24:00.00200021546333925 | Inform the site owner about the end of hypercare | - | Transition Lead | Pending
11 | 5 - Hypercare | 13 | 2021-02-25 | 11:24:00.00200021546333925 | PT0H10M0.000S | 2021-02-25T11:34:00.00200028531253575 | End of Hypercare | - | Site Owner | Pending
89 |  |  | - | - |  | -
90 |  |  | - | - |  | -
91 |  |  | - | - |  | -
92 |  |  | - | - |  | -
93 |  |  | - | - |  | -
94 |  |  | - | - |  | -
95 |  |  | - | - |  | -
96 |  |  | - | - |  | -
97 |  |  | - | - |  | -
98 |  |  | - | - |  | -
99 |  |  | - | - |  | -
100 |  |  | - | - |  | -
101 |  |  | - | - |  | -
102 |  |  | - | - |  | -
103 |  |  | - | - |  | -
104 |  |  | - | - |  | -
105 |  |  | - | - |  | -
106 |  |  | - | - |  | -
107 |  |  | - | - |  | -
108 |  |  | - | - |  | -
109 |  |  | - | - |  | -
110 |  |  | - | - |  | -
111 |  |  | - | - |  | -
112 |  |  | - | - |  | -
113 |  |  | - | - |  | -
114 |  |  | - | - |  | -
115 |  |  | - | - |  | -
116 |  |  | - | - |  | -
117 |  |  | - | - |  | -
118 |  |  | - | - |  | -
119 |  |  | - | - |  | -
120 |  |  | - | - |  | -
121 |  |  | - | - |  | -
122 |  |  | - | - |  | -
123 |  |  | - | - |  | -
124 |  |  | - | - |  | -
125 |  |  | - | - |  | -
126 |  |  | - | - |  | -
127 |  |  | - | - |  | -
128 |  |  | - | - |  | -
129 |  |  | - | - |  | -
130 |  |  | - | - |  | -
131 |  |  | - | - |  | -
132 |  |  | - | - |  | -
133 |  |  | - | - |  | -
134 |  |  | - | - |  | -
135 |  |  | - | - |  | -
136 |  |  | - | - |  | -
137 |  |  | - | - |  | -
138 |  |  | - | - |  | -
139 |  |  | - | - |  | -
140 |  |  | - | - |  | -
141 |  |  | - | - |  | -
142 |  |  | - | - |  | -
143 |  |  | - | - |  | -
144 |  |  | - | - |  | -
145 |  |  | - | - |  | -
146 |  |  | - | - |  | -
147 |  |  | - | - |  | -
148 |  |  | - | - |  | -
149 |  |  | - | - |  | -
150 |  |  | - | - |  | -
151 |  |  | - | - |  | -
152 |  |  | - | - |  | -
153 |  |  | - | - |  | -
154 |  |  | - | - |  | -
155 |  |  | - | - |  | -
156 |  |  | - | - |  | -
157 |  |  | - | - |  | -
158 |  |  | - | - |  | -
159 |  |  | - | - |  | -
160 |  |  | - | - |  | -
161 |  |  | - | - |  | -
162 |  |  | - | - |  | -
163 |  |  | - | - |  | -
164 |  |  | - | - |  | -
165 |  |  | - | - |  | -
166 |  |  | - | - |  | -
167 |  |  | - | - |  | -
168 |  |  | - | - |  | -
169 |  |  | - | - |  | -
170 |  |  | - | - |  | -
171 |  |  | - | - |  | -
172 |  |  | - | - |  | -
173 |  |  | - | - |  | -
174 |  |  | - | - |  | -
175 |  |  | - | - |  | -
176 |  |  | - | - |  | -
177 |  |  | - | - |  | -
178 |  |  | - | - |  | -
179 |  |  | - | - |  | -
180 |  |  | - | - |  | -
181 |  |  | - | - |  | -
182 |  |  | - | - |  | -
183 |  |  | - | - |  | -
184 |  |  | - | - |  | -
185 |  |  | - | - |  | -
186 |  |  | - | - |  | -
187 |  |  | - | - |  | -
188 |  |  | - | - |  | -
189 |  |  | - | - |  | -
190 |  |  | - | - |  | -
191 |  |  | - | - |  | -
192 |  |  | - | - |  | -
193 |  |  | - | - |  | -
194 |  |  | - | - |  | -
195 |  |  | - | - |  | -
196 |  |  | - | - |  | -
197 |  |  | - | - |  | -
198 |  |  | - | - |  | -
199 |  |  | - | - |  | -
200 |  |  | - | - |  | -
Gowni, Karunakar (Ext):
Since these are new sites, no existing cloudflare rules exists. @bikram to confirm.
Gowni, Karunakar (Ext):
@bikram please confirm if MVP has search feature?
Gowni, Karunakar (Ext):
Since these are new sites, no existing cloudflare rules exists. @bikram to confirm.
Gowni, Karunakar (Ext):
Assuming there will be no redirects required as it will be new site and not migration.
Gowni, Karunakar (Ext):
Assuming there will be no redirects required as it will be new site and not migration.
Gowni, Karunakar (Ext):
Is this part of MVP? If not then we can ignore this row for now.
Gowni, Karunakar (Ext):
Ignore this - Specific to Arctic
Gowni, Karunakar (Ext):
Ignore this - Specific to Arctic
Gowni, Karunakar (Ext):
Ignore this - Specific to Arctic
Gowni, Karunakar (Ext):
WE need information on cloudflare rules for each site if any to be setup.
Gowni, Karunakar (Ext):
Arctic Specific
Gowni, Karunakar (Ext):
Only in case of migration. Can ignore if not migration
Gowni, Karunakar (Ext):
Validate if applicable
Note on H14: Gowni, Karunakar (Ext): @bikram please confirm if MVP has search feature?
Note on H16: Gowni, Karunakar (Ext): Since these are new sites, no existing cloudflare rules exists. @bikram to confirm.
Note on H22: Gowni, Karunakar (Ext): Since these are new sites, no existing cloudflare rules exists. @bikram to confirm.
Note on H28: Gowni, Karunakar (Ext): Assuming there will be no redirects required as it will be new site and not migration.
Note on H33: Gowni, Karunakar (Ext): Assuming there will be no redirects required as it will be new site and not migration.
Note on H41: Gowni, Karunakar (Ext): Is this part of MVP? If not then we can ignore this row for now.
Note on H65: Gowni, Karunakar (Ext): Ignore this - Specific to Arctic
Note on H66: Gowni, Karunakar (Ext): Ignore this - Specific to Arctic
Note on H67: Gowni, Karunakar (Ext): Ignore this - Specific to Arctic
Note on H70: Gowni, Karunakar (Ext): WE need information on cloudflare rules for each site if any to be setup.
Note on H71: Gowni, Karunakar (Ext): Arctic Specific
Note on H72: Gowni, Karunakar (Ext): Only in case of migration. Can ignore if not migration
Note on H75: Gowni, Karunakar (Ext): Validate if applicable

## Issue Tracker
Arctic Site Launch Issue Tracker
ID | Summary | Description | Reporter | Importance | Remarks / Follow Ups
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Lookups
Status | Phase | Site | Issue Status
Pending | 1 - Pre-Launch | <sitename1-internalurl> | Urgent
In Progress | 2 - Dry Run | <sitename1> | High
Completed | 3 - Launch | <sitename2> | Medium
Cancelled | 4 - Rollback | <sitename> | Low
On Hold | 5 - Hypercare | dry-run654.novartis.com
Not Applicable